## Sheet1
2023 Action Plan
| Redmarley Tennis Club Committee Meeting |  |  |  | Meeting Date | 24/07/23
Next Meeting
Attendees | Jo Clarke Sally Loynes Robin Notley Kathy O'Keeffe Phill Primett Guy Savage | Apologies |  |  | Location & time | 19:00 Club House
Actions identified |  |  | Actions completed since last meeting |  | Total Number of actions completed
No. | Issue |  |  | Action & Status |  | Who | When | Status
Consolidated outstanding actions post floodlight project
31 | Play park accessibility proposal |  |  | What is the current plan. RJ to contact Neil Still no clarity at 23rd Feb 23 |  | RJ | 2023-04-01 | Closed
32 | Safeguarding Officer |  |  | Push BM to sort out her verification |  | RJ | 2023-02-01 | In Progress
37 |  |  |  | As part of the Crowdfunding for the floodlights, the Club agreed to plant trees in return for donations. Richard to raise with Parish Council re planting. Has been raised, no decision yet from Parish Council |  | RJ | 2023-01-03
39 |  |  |  | Sally outlined forthcoming events for the year which included a tennisathon, skittles night and auction of promises Review Auction of promises date as it clashes with the Rugby World Cup |  | Sally/Jo/ Caroline | 2023-04-04 | In Progress
51 | Communications |  |  | Caroline volunteered to look after this and her boyfriend will review/revamp the website and logo. It was agreed that Facebook needed regular postings. Caroline suggested 'meet the committee' posts going forward, then 'meet the member' as well as social events and coaching session advertising. Caroline to maintain the pavilion noticeboard. Review at next meeting |  | CB | Review progress at next meeting | In Progress
29/03/23
54 | Previous Actions |  |  | John Rowe will look after the Premier competition, Martin Lauricella will look after the club one. Caroline and Richard to meet with Martin tomorrow night |  | JR/ML RJ/CB/ML | 2023-03-30 | In Progress
56 |  |  |  | Josh will take some photos to update the site, Richard to take some at coaching. Agreement needed from parents |  | Josh RJ
76
77 | Forecast |  |  | The coaching fund is looking healthy and the sinking fund is just shy of its target. Level 2 coaches will get an increased allowance for Saturday mornings, as previously agreed. A 5% increase in membership is also planned for 2025. The forecast is cautious and the fundraising target is low. Membership income is also cautious but includes this year's increase. The club ends the year in a good financial position. The courts will be resurfaced in 2026 towards the end of the year. |  |  |  | Info
78
79 | 2023 Development |  |  | This is a requirement of the planning permission. The work will need to dovetail with the playground accessibility path which the parish council will take over from the club. Sally had notified Jo that Dave Malcolm would do this work and supply some of the materials. Sally, Guy and Dave to meet and take forward. All were in favour. |  | SL/GS/DM |  | Closed
80 |  |  |  | Meeting dates for 2023/4 have been provisionally set at 7 June, 6 September, 6 December and 27th March. RJ produced a standard agenda which will be held on the Google drive. Robin to chair the first meeting, Kathy sent her apologies |  | RN | 2023-05-03 | Closed
85 |  |  |  | Robin to change the number for the key caddy. This should be changed at the end of each season - Richard to add to the Process Control Chart for monitoring |  | RJ | asap
90 | 2023/24 Key Focus |  |  | Richard will outline this at the AGM |  | RJ | 2023-04-06 | Closed
91 |  |  |  | The committee thanked Richard for all the work he's undertaken as Chair |  |  |  | Info
93 | 2023-03-05
95 | Previous Actions |  |  | Safeguarding – There is a need to understand the talents of our members as one may have the right qualifications/experience to become the Welfare Officer. Kathy suggested this could be added to the membership form. Jo to talk to Barbara to see if she is still interested in the role but if so she will need to check her qualifications with the LTA Kathy said the key for football store is on a hook at the top right hand corner of the inside storeroom door, no label as yet |  | JC | 2023-05-14 | In Progress
98 | Financial Update - Year End |  |  | Robin is working on the final accounts |  | RN | end May | In Progress
100 | Parish Council & Playing Fields |  |  | 2023 Pavilion Landscaping Development Guy, Sally and Dave met up and Dave has the skill set. However, there is an insurance issue. The plan is to do the work in two halves to minimise disruption. Sally had spoken to the NFU and they thought the LTA should cover this if they were informed of all the details. A discussion was held and it was decided to see if Zurich could add it to our policy – Guy to ring. Sally to talk to Dave recosts and speak to NFU re adding the liability. |  | GS/SL | asap | Closed
101 |  |  |  | Shelter Reinstatement Sally said this should be tackled as an ongoing community issue rather than a Tennis Club one. The Shelter had been moved twice and then removed and it would never be anything other than a challenge for the community who are now even closer. There was also the possibility of drug paraphernalia being left in the shelter and littering the play park. She proposed teaming up with a group of representatives from The Vines to attend the meeting and outline the risks. Kathy to find out the date of the meeting and circulate around the committee. Sally had attended the meeting where it was not listed on the agenda but was raised by a number of attendees. Feelings are clearly still high and the matter will be added to the next agenda. |  | SL/ KO | asap | In Progress
115
116 | 24/07/23
117 | Previous Actions
118 | Safeguarding |  |  | Barbara had requested more information on what the role entails, which Robin will supply |  | RN
119 |  |  |  | Kathy to update the risk assessment template and store Sally's copy on the drive |  | KO | asap | Closed
120 | 2023 Pavilion landscaping development – path and steps construction project |  |  | Sally had spoken to a local landscaper she uses, Rob, and he is interested in the work, to commence on 14th August. He would charge for materials at cost plus a day rate, the estimate is ten days so £1,800 labour. He is not VAT registered and has his own insurance which will reduce our costs. Sally says he works incredibly hard and quickly. He will hire a digger for a couple of days for the steps and to level out the ground. Sally has spoken to Jeff Wheeler about the footpath closure which would require 8 week's notice and cost £1,300. Jeff recommended going ahead with caution amd Sally suggested a committee member be on hand when the digger is in use, to ask people to go around. Sally will also use her trailer to remove the rubble rather than hiring a skip and the excess soil will be used to bank up the rear of the pavilion. Rob will provide details of costs to Sally and once received, all were in favour of going ahead. |  | SL | asap | Closed
121 | Welfare Officer progress and update |  |  | as above
122 | Membership Update |  |  | The current membership figures were seen as a very good result and the committee thanked Richard for a brilliant job. Kathy said Laura from Tweenhills was also keen to join up and another membership had been received today |  |  |  | Info
123 | Coaching update |  |  | Richard provided a report which showed that coaching continued to go well, when the weather allowed and that it was being enjoyed by the coaches, coachees and spectators. Income was good and the coaching fund was building up nicely |  |  |  | Info
124 | Club Tournaments |  |  | RN to talk to Martin to see if his tournament can be rescued and completed. |  | RN | asap | Closed
125 |  |  |  | An autumn tournament was discussed to replace the premiership tournament and open to all. Caroline to email members to gauge interest. |  | CB | asap
126 | Financial Update |  |  | The total fund stands at £28,454 and is allocated £25,000 to club provision (sinking fund) £3,026 for coaching provision. 33% of coaching income goes into club funds and the balance goes to paying for courses and coaching provision. Committee members reported that Nailsworth, Minchinhampton and Beckford had all had artificial clay courts installed recently, costing £30,000k for two courts at one club. |  |  |  | Info
127 |  |  |  | Kathy to email the clubs to ask for costs, details of the supplier, were any LTA grants received, what are the annual costs and what is their lifespan? This will be discussed at next meeting. Kathy to add to the agenda. |  | KO | asap
128 | Year end |  |  | Total income is £11k per year and £30k is held in the sinking fund. The savings account had earned £80 in interest. This was seen as a reasonable financial position. |  |  |  | Info
129 |  |  |  | Diary note for September to look at electricity suppliers for changeover when the contract expires in December |  | RN | September
130 |  |  |  | Robin to chase Richard about adding activities cover to the insurance policy |  | RN | asap | Closed
131 |  |  |  | The Sumup account is open and charges a transaction fee of 1.63% but there is no charge for the account itself. RN to correct Kathy's email address for the second signature on the debit card application. |  | RN | asap
132 | Easyfundraising |  |  | Kathy to check earnings |  | KO | asap | Closed
133 | Social
134 | Tennis-a-thon out-takes |  |  | The event brought in £230 minus expenses |  |  |  | Info
135 | Events Agenda for the rest of 2023/24 year |  |  | The social committee to talk and come up with more ideas such a family friendly skittles and pizza event for the juniors with coaches to attend if possible. A quiz was also suggested. The difficulty in getting support from members was discussed with a number of suggestions made including charging more for match fees and tasking teams with raising a set amount in the way of their choice. The social committee to bring ideas to the next meeting and talk to team captains to get their buy in. An Auction of Promises would be a great way to raise a lot of money but would require buy in from all members and their friends to attend. It was agreed to hold this for the time being. |  | Social Committee | by next meeting
136 | Village Fete (August) |  |  | The event has been cancelled due to lack of interest. |  |  |  | Info
137 | 2023/4 Club Vision Discussion |  |  | Richard to present the coaching plan at the next meeting when the club vision will be discussed. Kathy to add to the agenda Coaching meeting is scheduled for 19th October, Richard to report back to meeting after that |  | KO | by next meeting | In Progress
138 | AOB
139 | Winter Mixed Doubles League |  |  | Phill to enter 3 teams again this year |  | PP | by mid August | Closed
140 |  |  |  | Caroline reported that Website work was ongoing but photos had been taken, |  |  |  | Info
141 |  |  |  | Club kit sales have been disappointing but it was suggested to relaunch it in spring and also offer unbranded versions. Kathy to add to next agenda |  | KO | by next meeting
142 |  |  |  | The Subgroups seem to be working well but a working party was probably needed in September – Guy to see what work needs to be carried out |  | GS | by mid August
143
144 | Date of Next Meeting |  |  | to be decided
145
146 | 20th September 2023
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241

## Sheet1 (2)
Action Plan
| Redmarley Tennis Club Committee Meeting |  |  |  | Meeting Date | 02.07.20
[5 empty] | Next Meeting | august
Attendees | Roger Apted Jo Clarke Richard Jenner Sally Loynes Robin Notley Phill Primett Kathy O'Keeffe Guy Savage Nigel Warren | Apologies | none |  | Location & time | Pavilion 19.30
Actions identified |  |  | Actions completed since last meeting |  | Total Number of actions completed
No. | Issue |  |  | Action & Status |  | Who | When | Status
1 | Lisa Jenner has been appointed Membership Secretary | [7 empty] | Key
2 | coaching |  |  | Jo to speak to Owen about Saturday morning coaching/summer camp |  | Jo | 08.07.20 |  | closed
3 |  |  |  | Contact LTA re grant for coaches |  | Richard | Wednesday 08.07.20 |  | not due
4 |  |  |  | Talk to Graham about Matt's accreditation |  | Kathy | Wednesday 08.07.20 |  | overdue
5 |  |  |  | Internet research for kid's coaches and funding |  | Sally | Wednesday 08.07.20
6 |  |  |  | Talk to Hartpury and Cirencester Colleges |  | Nigel | Wednesday 08.07.20
7 |  |  |  | Talk to John Rowe further about coaching |  | Jo | Wednesday 08.07.20
| Subscriptions |  |  | discount of 75% across the board, nice email to members giving option to pay full amount if they can. Amend membership form to reflect this |  | Richard/Nigel Kathy
|  |  |  | discount of 75% across the board, nice email to members giving option to pay full amount if they can. Amend membership form to reflect this |  | Richard/Nigel Kathy
4 | Subscriptions |  |  | discount of 75% across the board, nice email to members giving option to pay full amount if they can. Amend membership form to reflect this |  | Richard/Nigel Kathy
5 | Membership |  |  | finder's fee to be announced after subs have been requested, to be sent out as part of an initiative remove discount for new members |  | Kathy | end July
6 | Finance |  |  | HSBC change of signatories |  | Kathy | ongoing
7 | Court maintenance |  |  | work to be carried out, two quotes to be sourced ask Pete Hewett to repair the court netting where possible |  | Richard Guy | 2021-04-01
8 | Club kit |  |  | Are they ethically sourced make contact with owners and source typeface everything over £20 to stay the same, under to be increased by £2 |  | Richard Sally
9 | pavilion and landscaping |  |  | Bell's will connect the drains, hope to start in 2-3 weeks
10 | landscaping |  |  | quote for £11,500. |  | Guy | ongoing
11 | Grass cutting |  |  | rota to be drafted |  | Guy
12 | floodlights |  |  | liz to be thanked at AGM |  | Richard
13 |  |  |  | Quote up to 35,000, LTA Grant & loan of 75% of cost, we cover 25%
14 | safeguarding policy |  |  | onto website |  | kathy
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34