## Sheet1
2023 Action Plan
| Redmarley Tennis Club Committee Meeting |  |  |  | Meeting Date | Tuesday, 9th January 2024
[5 empty] | Next Meeting | Wednesday 6th March 2024
Attendees | Caroline Bennett Jo Clarke Sally Loynes Robin Notley Kathy O'Keeffe Guy Savage | Apologies | Bernie Davies Phill Primett |  | Location & time | 18.00 Club House
Actions identified
No. | Issue |  |  | Action & Status |  | Who | When | Status
170 | 1st November 2023
171 | Previous Actions
172 | Safeguarding -118 |  |  | Club has re-registered and Richard continues to stand in as Welfare Officer for now. Barbara is happy with the role details and will now register with the LTA with her Church DBS details. Supply log in details to Barbara. |  | RN | November | In Progress
173 | Autumn Premier Tournament (125) CB |  |  | Carry Forward |  | All | January | Closed
174 | Shelter reinstatement Update (101) SL |  |  | No further Progress |  |  |  | Info
175 | Court Resurfacing KO |  |  | Clubs with Synthetic Matting - Nailsworth and Ledbury - arrange visit/club game to try out Clubs with Artificial Clay - Beckford and Chalford - arrange visit/club game to try out Ballpark costings to change to above to be obtained - Grimshaws? |  | PP/ CB/ RN | March | In Progress
176 | Electricity Supply Change (129) RN |  |  | Contracts ends 11th Dec. Quotes obtained from Bionic (Business power consolidator) and new rates from best supplier are from EON @ Standing Charge £0.56/day Unit rate £0.288 KWH. 36 month contract. Club annual costs will reduce from £900 to £640. 2022 comparable costs £560 Go ahead with new contract with BIONIC. New contract in place saves £430 pa |  | RN | November | Closed
177 | Autumn Working Party (142) GS |  |  | Carry Forward - Winter working party |  | GS | January | Info
178 | Finance Update |  |  | 2022 Finances signed off by Duncan Woodger Accountancy - File. Draft state of the Finances for 2023/4 presented and updated summary is as follows: Current Income £9.6k: Current Total Costs £6.4k: Surplus £3.1k Forecast Income £10.8k: Forecast Total Costs £8.9k: Surplus £2.0k Budget Income £11.8k: Budget Costs £6.4k: Surplus £5.3k Projected Funds Shortfall £3.5k at Year end. This is due to the unbudgeted cost of replacing and upgrading the steps and patio area and is a one off. However, to ensure adequate funds are available for court surfacing replacement in 2026 this shortfall needs to be re-couped. Initiatives to achieve this are: Full cost charging for LTA League matches to continue for summer leagues / Maintain as much cash in the interest earning savings account as possible / Progress roll out of Easyfundraising initiative / Review social events - more smaller group events to raise money etc. Drive to increase membership but keep club fees the same (a 5% increase will only bring in £324) due to the risk of losing members. |  | RN | Next Meeting | In Progress
179 | Power costs |  |  | Currrently being monitored - awaiting payments from home LTA matches - Review end of LTA Winter league |  | RN | Jan 24 | In Progress
180 | SumUp account/card |  |  | HSBC Debit Card obtained. Sum up account opened. Cost of Sum up machine £42.99 and 1.69% charge to transactions. Purchase for next Social event. Square app has been set up and is working well. 1.72% charge, £5 charged at the quiz. |  | RN | 1st Dec | Closed
181 | Membership update |  |  | 6 winter memberships taken out - income £233 |  |  |  | Info
182 | Coaching update |  |  | Graham Baum signed as Level 3 coach for LTA registration. Club has 2 x L2 coaches and 1 x L2 in progress. Phill has started his L3 accreditation |  |  |  | Info
183 | Safeguarding |  |  | All products moved to Rear Store |  |  |  | Info
184 | Risk management |  |  | Inspection carried out and small maintenance tasks noted. Urgent items - PAT testing to be carried out before 9th Dec - Contact Slatters. Floodlight time clock to be adjusted for GMT. |  | GS/RN | ASAP | In Progress
185 | Social events update |  |  | Quiz & Pudding night set for Friday 8th Dec 7pm for 7.17pm start. Cost £7.50 pp. Mike M & Village Hall - check poss clash with Village Xmas sale set up for 9th Dec. Marketing to be done asap - Website / Watsap groups / Email / Posters. Event raised circa £500 |  | JC/CB | ASAP | Closed
186 | Tuesday night social winter format |  |  | Late start 7.30pm Social tennis to commence - Active player required to manage WhatsApp group Handled via WhatsApp group and is working well |  | PP | ASAP | Closed
187 | New Committee Members |  |  | Committee welcomed the news that Bernie is joining us and will represent Parents' interests. |  |  |  | Info
188 | Any Other Business |  |  | An issue with winter league team players matching was discussed following a complaint from one of the players. It was agreed that little could be done due to the disparity between male and female numbers and the need to ensure all players were selected. |  |  |  | Closed
189 | AOB - cont |  |  | RN reported on Zoom meeting with LTA regional clubs - highlighted current LTA push to introduce an onerous list of requirements for clubs to adhere to. To be presented and discussed at next meeting |  | RN | January | In Progress
190 | Next Meeting Date |  |  | 9th January 2024 6.00pm
191
192 | 9th January 2024
193 | Coaching Update (Richard Jenner) |  |  | Richard upated the committee on six new elements which will be trialled to encourage more take up of tennis and therefore hopefully increase membership. These included cardio tennis; tennis express; focused improvement sessions; game development clinics and getting match ready. The proposals were well received and Richard will now focus on the first three and discuss logistics and costings in order to start early in the season. A copy of Richard's slides is held on the drive |  | RJ | Next Meeting
194 | Finance Update |  |  | Robin circulated a finance update which showed a much improved position. The shortfall forecast in November 2023 was £3,500 but now stands at £1,344. It was estimated this could easily be recouped in the coming season with the increased income streams (lighting charges, easyfundraising) and it was felt the current lighting charges would result in a profit given the decrease in electricity costs |  |  |  | Info
195 | PAT Testing |  |  | This is still outstanding Robin to get the contact details for Slatters from Richard and arrange the PAT testing |  | RN | ASAP
196 | Welfare/Safeguarding Update |  |  | No progress yet made. Robin to discuss with Barbara to get her in place |  | RN | ASAP
197 | Risk Management |  |  | Kathy conducted the inspection and noted that there are still patches of moss around the playing areas and peripherary. A further treatment will be carried out when the weather warms up. The crack at the far side of the courts is not seen as an issue at present. In the pavilion there is a crack in one of the chair backs. |  | GS | February
198 |  |  |  | Kathy to email the rota to the committee and attach a copy of the last inspection and a blank inspection form |  | KO | by end January | Closed
199 |  |  |  | The window catch in the toilet needs replacing as it is broken |  | GS | February
200 | Social Events |  |  | The Rose and Crown are happy to host a meal type event but for now it was decided to hold the AGM there on Thursday 11th April with pizza and skittles. Date confirmed |  | SL | by end January | Closed
201 |  |  |  | AGM Date to be circulated to members as soon as it is booked |  | KO | by end January
202 |  |  |  | Another Curry night was suggested or maybe an Italian with Tewkesbury as a possible venue. Ideally to be held in February/March |  | Social Committee | ASAP
203 |  |  |  | Kathy is planning to hold the Vintage Afternoon Tea on Saturday 2nd March, date to be confirmed. 2nd March is confirmed |  | KO | ASAP | Closed
204 |  |  |  | Kathy is organising a Sunday Social Tournament for the 9am coaching group to be held one afternoon in February 18th February is in the diary, 10 participants have booked in |  | KO | ASAP | Closed
205 | Club Tournament |  |  | It was agreed to revert to the old tournament format. Jo and Caroline agreed to run |  | JC/CB | to start in May
206 | Any Other Business
207 | - Club Secretary |  |  | Kathy reported that she will stand down as Club Secretary at the AGM. She will continue to help Richard with the coaching and to help out with Sunday socials/tournaments. |  |  |  | Info
208 |  |  |  | Kathy to circulate job description with minutes. |  | KO | ASAP | Closed
209 |  |  |  | Robin and Kathy to talk about advertising the role to members in the near future. |  | RN/KO | 22/01/24 | Closed
210 | - Over 60s League |  |  | Kathy reported that Ann and Nigel Russell had joined Winchcombe TC and have started playing in the LTA's Over 60's leagues. They are enjoying this friendly day-time tennis. Kathy proposed setting this up for the summer season to ensure that those who want to play league tennis get more games than at present. Kathy to ascertain interest and set up for the ladies and a mixed team and ask Phill to enter into the leagues. Further investigation showed this to be a winter format. Kathy to follow up in September |  | KO | September | In Progress
211 | - Easyfundraising |  |  | This raised a further £32 over Christmas and recruited 3 new supporters. TUI holidays are offering a chance to win the cost of a holiday (up to £3,000) by booking using the easyfundraising link - Kathy to email members as an incentive to sign up |  | KO | by end January | Closed
212 |  |  |  | 17 people have signed but haven't earned anything yet which could be because they haven't opted for the reminder to flash up on screen when they're shopping. Kathy to email them explaining how to do it |  | KO | by end January | Closed
213 | - Trophies engraved |  |  | 2 trophies for the Kay Smith Tournament winners - Jill Williams and Yvette Holborow are to be engraved as well as other cups won in this year's tournament |  | RN | by end March
214 | - Job descriptions |  |  | Robin to talk to the subgroups outside the committee to gain a better understanding of how they work and ensure they have a voice back into the committee. |  | RN | by end March
215 | - Sub Groups |  |  | Sally to do a cleaning rota |  | SL | by end January | Closed
216 |  |  |  | Guy to do a grass cutting rota |  | GS | by end January
217 |  |  |  | Robin confirmed he is happy to stay on as Chair and Treasurer for the time being |  |  |  | Info
218 | Proposed Dates for This Year's Meetings |  |  | Wednesday 6th March |  |  |  | Info
219 |  |  |  | Thursday 11th April – AGM |  |  |  | Info
220 |  |  |  | Wednesday 1st May |  |  |  | Info
221 |  |  |  | Wednesday 3rd July |  |  |  | Info
222 |  |  |  | Wednesday 4th September |  |  |  | Info
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242

## Sheet1 (2)
Action Plan
| Redmarley Tennis Club Committee Meeting |  |  |  | Meeting Date | 02.07.20
[5 empty] | Next Meeting | august
Attendees | Roger Apted Jo Clarke Richard Jenner Sally Loynes Robin Notley Phill Primett Kathy O'Keeffe Guy Savage Nigel Warren | Apologies | none |  | Location & time | Pavilion 19.30
Actions identified |  |  | Actions completed since last meeting |  | Total Number of actions completed
No. | Issue |  |  | Action & Status |  | Who | When | Status
1 | Lisa Jenner has been appointed Membership Secretary | [7 empty] | Key
2 | coaching |  |  | Jo to speak to Owen about Saturday morning coaching/summer camp |  | Jo | 08.07.20 |  | closed
3 |  |  |  | Contact LTA re grant for coaches |  | Richard | Wednesday 08.07.20 |  | not due
4 |  |  |  | Talk to Graham about Matt's accreditation |  | Kathy | Wednesday 08.07.20 |  | overdue
5 |  |  |  | Internet research for kid's coaches and funding |  | Sally | Wednesday 08.07.20
6 |  |  |  | Talk to Hartpury and Cirencester Colleges |  | Nigel | Wednesday 08.07.20
7 |  |  |  | Talk to John Rowe further about coaching |  | Jo | Wednesday 08.07.20
| Subscriptions |  |  | discount of 75% across the board, nice email to members giving option to pay full amount if they can. Amend membership form to reflect this |  | Richard/Nigel Kathy
4 | Subscriptions
5 | Membership |  |  | finder's fee to be announced after subs have been requested, to be sent out as part of an initiative remove discount for new members |  | Kathy | end July
6 | Finance |  |  | HSBC change of signatories |  | Kathy | ongoing
7 | Court maintenance |  |  | work to be carried out, two quotes to be sourced ask Pete Hewett to repair the court netting where possible |  | Richard Guy | 2021-04-01
8 | Club kit |  |  | Are they ethically sourced make contact with owners and source typeface everything over £20 to stay the same, under to be increased by £2 |  | Richard Sally
9 | pavilion and landscaping |  |  | Bell's will connect the drains, hope to start in 2-3 weeks
10 | landscaping |  |  | quote for £11,500. |  | Guy | ongoing
11 | Grass cutting |  |  | rota to be drafted |  | Guy
12 | floodlights |  |  | liz to be thanked at AGM |  | Richard
13 |  |  |  | Quote up to 35,000, LTA Grant & loan of 75% of cost, we cover 25%
14 | safeguarding policy |  |  | onto website |  | kathy
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34